Implementation Plan – HOVUCA

Project Title: A Policy analysis and advocacy project to engage AGYW in National HIV programmes and Global Fund Processes

| Objectives | Activities |  | June | July | Aug | Sept | Oct. | Nov. | Dec | Jan. | Feb. | March |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective 1 To open a research space to give AGYW the opportunity to study the national HIV policy/guidelines, analyze them, identify policy gaps and advocate for HIV policy reforms that gives AGYW an enabling environment to access HIV services with ease as well as greater involvement in the design and implementation of national HIV Programmes | 1. | Preliminaries for project kickoff - Obtaining administration documents (permit) if applicable (documents like permits to carry out public events, this is because sometimes we required permit to carry certain public activity) - Organizing a project kickoff meeting for HOVUCA staff and project team members and volunteers. |  |  |  |  |  |  |  |  |  |  |
|  | 2. | Advocacy speech writing competition on national HIV policies |  |  |  |  |  |  |  |  |  |  |
|  |  | - Meeting for drawing up of modalities for the competition |  |  |  |  |  |  |  |  |  |  |
|  |  | - Digital flyer for publication/advertising of the competition |  |  |  |  |  |  |  |  |  |  |
|  |  | - Review of submitted papers for selection finalist |  |  |  |  |  |  |  |  |  |  |
|  | 3 | Briefing meeting where finalist will present their papers in the presence of policy makers and award of prizes |  |  |  |  |  |  |  |  |  |  |
| Objective 2 To Educate/train in-school and out-of-school AGYW on HIV and related policies and build their capacities on leadership skills and public speaking to raise their self-esteem and confidence to better handle public advocacy. | 1. | Continuation of the ambassador forum |  |  |  |  |  |  |  |  |  |  |
|  | 2. | Establishment and running adolescent girls HIV Clubs in 3 schools |  |  |  |  |  |  |  |  |  |  |
|  | 3. | Preparation workshop for running of the clubs |  |  |  |  |  |  |  |  |  |  |
|  | 4. | Advocacy Press Conference on barriers to accessing HIV services by trained in-school and out-of-school AGYW of the ambassador forum (high, university students) |  |  |  |  |  |  |  |  |  |  |
| Objective 3. To engage AGYW in a rigorous advocacy for the availability and accessibility and affordability of HIV counselling, testing and treatment at all levels(from remote communities to district, divisional and national levels) | 1. | Advocacy for availability of HIV counseling, testing and treatment for AGYW at all levels |  |  |  |  |  |  |  |  |  |  |
| Objective 4 To ensure the participation of AGYW in national HIV programmes/meetings like with RTG for the fight against HIV/AIDS as well as some HIV meetings with related line ministries and Global Fund Processes related meetings. | 1. | Participation of AGYW in National HIV programme – different planning or technical meetings at district, Divisional or national level and meetings of the CSOs of CCM and other related CCM meetings |  |  |  |  |  |  |  |  |  |  |
|  |  | Monitoring and Evaluation |  |  |  |  |  |  |  |  |  |  |
|  |  | Documentation and reporting |  |  |  |  |  |  |  |  |  |  |