Request for Support to:

strengthen the work Hope for Vulnerable Children Association (HOVUCA) is

doing on the project:

“Reduction of the incidence of HIV amongst adolescent girls in schools through improve communication and leadership skills of adolescent girls and young women (AGYW) in Sexual and Reproductive Health and advocacy in the Mfoundi Division”

SUBMITTED To

UNFPA

by

HOPE FOR VULNERABLE CHILDREN ASSOCIATION (HOVUCA)

Reg. N0 00001065/ARDA/J06/BAPPA

Head Office: Simbock, Yaounde

P.O.Box 8257, Yaounde

Email: contact@hovuca.org  /  eve_lum@hovuca.org

Website: https://hovuca.org

Tel: (+237) 677 789 855

Contact Person: LUM Evelyne

POSITION: Executive Director

Terms of Reference for this Request to UNFPA

- Introduction.

HER Voice is a project funded by The Global Fund to fight HIV and ViiV Healthcare Positive Action and implemented by Global Network of Young People Living with HIV (Global) With Hope for Vulnerable Children Association (HOVUCA) as subgrantee in Cameroon. The HER Voice Fund project’s strategic objective is to strengthen the meaningful engagement and leadership of adolescent girls and young women (AGYW) in decision making spaces with the aim of reducing HIV incidence and improving the broader health, wellbeing and rights of AGYW. HOVUCA has been implementing HER Voice fund project since 2020. This year (2023), HOVUCA has received another small grant from Y+Global to continue implementation of activities aimed at promoting sexual and reproductive health (SRH) knowledge for adolescent girls in secondary schools and also to fight against gender inequality, gender-based violence and harmful norms inhibiting the enjoyment of the sexual and reproductive health and rights (SRHR) of adolescent girls and young women. Among other activities of this year, we will be imparting knowledge on sexual and reproductive health, GBV, Human rights to adolescent girls in schools. For the past 2 years of delivering SRH and comprehensive sexuality education (CSE) to adolescents, we have had just a short period of time to teach and not covering the topics to satisfaction, this has been partly due to limited funds. This year, we will like to strengthen this activity in schools by extending the teaching period from 8 sessions to 16 sessions and this will enable us to give meaningful package to adolescent enough to bring the required knowledge good enough for them to make informed choices about their health and rights. We will also like to create a great impact by engaging key stakeholder, adding more schools, and training more peer educators. Therefore, HOVUCA is soliciting the support of UNFPA to strengthen the HER Voice activities based on the following objectives

- Overall Objective

The overall objective of this request is to strengthen the HER Voice project activity for adolescent girls in school through the provision of comprehensive sexuality education which is directly in line with the Education Plus Initiative that UNPFA alongside UNAIDS, UNICEF, UN Women and UNESCO are advocating for.

Specific objectives of this request include:

- To mobilize and engage key stakeholder in a discussion on the possibility of integrating sexual and reproduction health, comprehensive sexuality education in the school curricular

- To empower 24 adolescent girls and young women in and out of schools with knowledge on comprehensive sexuality education and build their leadership skills to become peer educators and advocates for adolescent girls sexual and reproductive health rights.

- To collaborate with education institutions in Yaounde 3, 6, and 7 and impart knowledge and skills to 2000 adolescent girls in 8 public and private schools about their sexual, reproductive and health rights for four months.

- To build the capacities of 24 teachers selected from 8 schools on the provision of  sexuality education to adolescents aimed at the sustainability of the project after it ends.

3. Activities under this request include:

  - Organize and conduct a one-day consultation meeting with key stakeholders including decision/policy maker to advocate for the integration of comprehensive sexuality education in the school curricular. This consultation meeting will take place at Djeuga Palace Hotel and will bring together vital stakeholders from frontline ministries like – Ministries of Basic and Secondary Education, health, women’s empowerment as well as parliamentarians and UN partners who are championing the education plus initiative. Adolescent girls and young women themselves will be part of this consultation meeting.

  - Conduct a 2 days empowerment workshop to build the leadership skills of adolescent girls and young women in and out of school to become peer educators and advocates for adolescent girls sexual, reproductive and health rights. This 2- days empowerment workshop will take place in Mbalmayo to ensure participants focus on the training. It will bring together 24 adolescent girls and young women, 16 out of school and 8 in-school adolescents girls selected from the 8 schools where comprehensive sexuality education knowledge is delivered. This is to ensure the participation of adolescent girls and young women in the project that concerns them by teaching their peers and leading awareness and advocacy for their health rights in their different schools. During this empowerment workshop, we will also have some of the key stakeholders who participated in the consultation meeting to be part of this empowerment workshop to ensure they follow-up the different steps of the advocacy.

  - Teaching of comprehensive sexuality education to adolescent girls in schools by the peer educators. This activity will go on simultaneously in 8 selected secondary schools in Yaounde 3,6 and 7 and the 16 AGYW peer educators will be delivering the sexual and reproductive health lessons to their peers in the selected schools. The teaching program will use club hours in school that are running school clubs and free periods in schools that are not operating club activities.

  - Capacity building for teachers on the provision of sexuality education to adolescent girls in schools. Due to culture, teachers like parents sometimes resist sexuality education in schools. Therefore, this workshop will create awareness to teachers of the importance of sex education to especially adolescents’ girls. However, this activity will take place out of Yaoundé in Mbalmayo and will bring together 24 teachers – 3 teachers form each of the 8 schools selected for teaching sexuality education to adolescent girls. They will also be empowered on the delivery ethics of comprehensive sexuality education to adolescents. This is also to ensure that after the project, the teachers will continue to teach new students.

4. Outcomes.

  - Increased political commitment and support on the integration and provision of sexual and reproductive health and comprehensive sexuality education in schools for adolescents and girls.

  - Increased leadership skills and confidence for 24 in and out of school adolescent girls and young (AGYW) to impart knowledge on comprehensive sexuality education  to their peers and increased skills in developing advocacy messages by the trained school girls.

  - Increase knowledge on sexual, reproductive and health rights for 2000 adolescent girls in schools, hence reduced STIs/HIV infections and unwanted pregnancies; improved self-esteem and self-efficiency as well as increase age of sexual debut, safe sex and condom use.

  - Increase knowledge for 24 trained teachers on age-appropriate knowledge on adolescent sexual and reproductive health, HIV and GBV prevention and teaching skills in delivering lessons to adolescent girls in schools

- Proposed Implementation schedule from June 2023 to February 2024

| month | June 2023 |  |  |  | Jul. 2023 |  |  |  | Aug. 2023 |  |  |  | Sept. 2023 |  |  |  | Oct. 2023 |  |  |  | Nov. 2023 |  |  |  | Dec. 2023 |  |  |  | Jan. 2024 |  |  |  | Feb. 2024 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Week | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |
| Activities Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct a one-day consultation meeting with key stakeholders to advocate for the integration of comprehensive sexuality education in the school curricular |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct a 2 days empowerment workshop to build the leadership skills of adolescent girls and young women in and out of school to become peer educators and advocates for adolescent girls sexual, reproductive and health rights. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Capacity building for teachers on the provision of sexuality education to adolescent girls in schools. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Teaching of sexual and reproductive health and rights to adolescent girls in schools by the peer educators |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Monitoring and Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Reporting to donor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Budget Estimate

| Activity Name | Unit of Measurement | Quantity | Unit Cost FCFA | Frequency | Total Cost FCFA |
| --- | --- | --- | --- | --- | --- |
| Conduct a one-day consultation meeting with key stakeholders to advocate for the integration of comprehensive sexuality education in the school curricular |  |  |  |  |  |
| Hall (Djeuga Palace Hotel) | Per day | 1 | 160,000 | 1 | 160,000 |
| Meal (Buffet Junior) | Per person | 26 | 13,500 | 1 | 351,500 |
| Transport for Participants | Per person | 26 | 5,000 | 1 | 130,000 |
| projector | Per day | 1 | 35,000 | 1 | 35,000 |
| Writing Material for Participants (file, pen and block note) | Per person | 26 | 1,000 | 1 | 26,000 |
| Rollup banner |  | 1 | 50,000 | 1 | 50,000 |
| Subtotal |  |  |  |  | 752,500 |
| Conduct a 2 days empowerment workshop to build the leadership skills of adolescent girls and young women in and out of school to become peer educators and advocates for adolescent girls sexual, reproductive and health rights. (Place of training: Mbalmayo) |  |  |  |  |  |
| Transport | Per person | 34 | 10,000 | 1 | 340,000 |
| Coffee break | Per person | 34 | 3,500 | 2 | 238,000 |
| launch | Per person | 34 | 5,000 | 2 | 340,000 |
| Teaching aid Material (markers, flip charts, cardboard papers) | Lump sum |  | 15,000 |  | 15,000 |
| Writing materials for participants (Folder, pen and notebook) | Per person | 34 | 1700 | 1 | 57,800 |
| Seminar Room (hire including project and sound system) | Per day | 1 | 100,000 | 2 | 200,000 |
| Facilitators fee | Per facilitator | 1 | 50,000 | 2 | 100,000 |
| Rollup banner | Per bannar | 1 | 50,000 | 1 | 50,000 |
| Production of training manual | Per copy | 34 | 2,500 | 1 | 85,000 |
| Per diem for participants | Per person | 34 | 40,000 | 3 | 4,080,000 |
| Subtotal |  |  |  |  | 5,505,800 |
| Teaching of Sexual and reproductive health and rights to adolescent girls in schools by peer educator |  |  |  |  |  |
| Teaching session allowance for out of school AGYW peer educators | Per peer educator | 16 | 5,000 | 16 | 1,280,000 |
| Development, design and printing of talking compounds (messages) | Per banner/poster | 8 | 20,000 | 1 | 160,000 |
| Support allowance for the 8 in-school advocates (for airtime to do research and put on notice board current information on the sexual and reproductive health of adolescents) | Per advocate per month | 8 | 10,000 | 4 | 320,000 |
| Small presents (gifts) like cups orbowls with awareness CSE messages Stickers | Per girls | 2000 | 500 | 1 | 1,000,000 |
| Subtotal |  |  |  |  | 2,760,000 |
| Capacity building for teachers on the provision of comprehensive sexuality education (CSE) to adolescent girls in schools. (Place of training: Mbalmayo) |  |  |  |  |  |
| Transport | Per participant | 29 | 10,000 | 1 | 290,000 |
| Coffee break | Per person | 29 | 3,500 | 2 | 203,000 |
| Lunch | Per person | 29 | 5,000 | 2 | 290,000 |
| Facilitators allowance |  | 2 | 50,000 | 2 | 200,000 |
| Development of Handout on CSE for teachers |  | 1 | 100,000 | 1 | 100,000 |
| Production of copies of CSE handouts for teachers | Per copy | 29 | 2500 | 1 | 72,500 |
| Teaching aid Material (markers, flip charts, cardboard papers) | Lump sum |  | 15,000 | 1 | 15,000 |
| Writing materials for participants (folder, pen, notebook) | Per person | 30 | 1700 | 1 | 51,000 |
| Banner |  | 1 | 15,000 | 1 | 15,000 |
| Per diem | Per participant | 29 | 40,000 | 3 | 3,480,000 |
| Subtotal |  |  |  |  | 4,716,500 |
| Grand Total |  |  |  |  | 13,753,800 |