Request for Support to:

Impact Knowledge on Comprehensive Sexuality Education (CSE) to Adolescent Girls in schools in Yaounde

Submitted to the Director of UNAIDS

By

HOPE FOR VULNERABLE CHILDREN ASSOCIATION (HOVUCA)

Reg. N0 00001065/ARDA/J06/BAPPA

Head Office: Simbock, Yaounde

P.O.Box 8257, Yaounde

Email: contact@hovuca.org  /  eve_lum@hovuca.org

Website: https://hovuca.org

Tel: (+237) 677 789 855

Contact Person: LUM Evelyne

POSITION: Executive Director

Terms of Reference for this Request to the Director of UNAIDS

BACKGROUND

Although Cameroon has seen a reduction in the HIV prevalence rate over the years. Adolescents and young people (10-24 years old) who represent 62.4% of the national population have been denied Comprehensive Sexuality Education (CSE) which could enable them gain knowledge, explore values and attitudes, and develop the skills they need to make conscious, healthy and respectful choices about relationships and sexuality.

Due to inadequate knowledge on CSE for adolescents, Sexual and Reproductive Health (SRH) Vulnerability in Colleges and High Schools and in communities in Cameroon is real. Identified reproductive health issues for especially adolescent girls include: High rate of HIV where adolescent girls and young women (AGYW) aged 15 and 24 are 9 times more contaminated with HIV than young boys in the same range age (MINANTE 2021); early sexual intercourse, unwanted early pregnancy, STIs, early marriages, sexual violence and abuse, clandestine abortions, and multiple partners. The above issues pertain to sexual health and sexuality and are areas comprehensive sexuality education (CSE) would address.

HOVUCA has got the experience impacting girls in schools which knowledge on CSE which is one of the pillars of the Education Plus Initiative. Hence, fulfilling the SRHR of adolescent girls. This was done through the collaboration and financial support of UNFPA and Y+Global (in the HER Voice Fund project) and enabled  HOVUCA to reach 5,276 adolescent school girls in 14 different schools in the Mfoundi Division who are making conscious decisions about their sexual and reproductive health and rights. However, there are still many girls in different schools who are in need of this CSE knowledge and who do not have access. HOVUCA has identified yet 5 other schools in the Mfoundi Division who are not offering CSE/SRH education and reason why we are requesting this financial support to impact knowledge on CSE to adolescent girls to enable them make informed choices about their sexual and reproductive health and rights and reduce the incidence of HIV, unwanted pregnancies and unsafe abortions.

We are therefore soliciting for financial support to impact knowledge on comprehensive sexuality education to adolescent girls in schools in 5 additional schools Yaounde targeting at least 750 school girls

OVERALL OBJECTIVE

The overall objective of this request is to enable adolescent girls make conscious decisions about the sexual and reproductive health and rights (SRHR) through the provision of comprehensive sexuality education (CSE) for adolescent girls in schools in Yaounde by November 2024.

Specific objectives of this request include:

- To empower 16 adolescent girls and young women with knowledge on comprehensive sexuality education and build their leadership skills to become peer educators and deliver CSE to their peers in schools by July 2024

- To collaborate with 5 education institutions and sensitize at least 750 adolescent girls on comprehensive sexuality education for two months (October and November 2024)

ACTIVITIES AS PER OBJECTIVE

Objective 1: To empower 16 adolescent girls and young women with knowledge on comprehensive sexuality education and build their leadership skills to become peer educators and deliver CSE to their peers in schools by July 2024

Activity 1: Conduct a 2 days empowerment workshop to build the leadership skills of adolescent girls and young women to become peer educators

This empowerment workshop will take place in Mbalmayo for 2 days and will involve 20 persons (16  adolescent girls and young women, 3 HOVUCA staff and 1 resource person). The purpose is to trained adolescent girls and young women as peer educators so that they can transfer knowledge on comprehensive sexuality education to their peers in schools later on.

Objective 2: To collaborate with 5 education institutions and sensitize at least 750 adolescent girls on comprehensive sexuality education for two months (October and November 2024)

Activity 2: Sensitization of adolescent girls in schools on comprehensive sexuality education (CSE).

This activity will involve16 AGYW peer educators delivering CSE and key areas of sexual and reproductive health lessons to their peers in 5 selected schools in Yaounde (Yaounde III, VI and VII) The sensitization program will use club hours in school that are running school clubs and free periods in schools that are not operating club activities. Sensitization will take once a week in each school and the and this activity will cover 8 weeks.

EXPECTED RESULTS.

- 16 adolescent girls and young women (AGYW) with knowledge, skills and confidence to impart knowledge on comprehensive sexuality education to their peers in schools.

- At least 750 adolescent girls in schools have the ability and competence to make informed choices about their sexual and reproductive health and rights.

- Proposed Implementation schedule from August 2023 to March 2024

| month | July 2024 |  |  |  | August 2024 |  |  |  | September 2024 |  |  |  | October 2024 |  |  |  | November 2024 |  |  |  | December 2024 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Week | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |
| Activities Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1: Mobilization and Recruitment of participants and logistical arrangements for the peer education training workshop |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2: Conduct a 2 days empowerment workshop to build the leadership skills of 16 adolescent girls and young women to become peer educators |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3: Formal visit to the education institutions to have a conversation with school authority to agree on appropriate time/periods to carry out the sensitization exercise |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 4: Sensitization of adolescent girls in schools on comprehensive sexuality education (CSE). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Monitoring and Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Reporting to donor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

BUDGET ESTIMATE

| Activity Name | Unit of Measurement | Quantity | Unit Cost FCFA | Frequency | Total Cost FCFA |
| --- | --- | --- | --- | --- | --- |
| Activity 1: Conduct a 2 days empowerment workshop to build the leadership skills of 16 adolescent girls and young women to become peer educators |  |  |  |  |  |
| Transport | Per person | 20 | 5,000 | 1 | 100,000 |
| Coffee break | Per person | 20 | 3,500 | 2 | 140,000 |
| launch | Per person | 2 | 5,000 | 2 | 200,000 |
| Teaching aid Material (markers, flip charts, cardboard papers) | Lump sum |  | 20,000 |  | 20,000 |
| Writing materials for participants (Folder, pen and notebook) | Per person | 20 | 2000 | 1 | 40,000 |
| Seminar Room (hire including project and sound system) | Per day | 1 | 100,000 | 2 | 200,000 |
| Facilitators fee | Per facilitator | 1 | 50,000 | 2 | 100,000 |
| Rollup banner | Per banner | 1 | 50,000 | 1 | 50,000 |
| Production of training manual | Per copy | 20 | 2,500 | 1 | 50,500 |
| Per diem for participants | Per person | 20 | 40,000 | 3 | 1,600,000 |
| Transport/fuel to do arrangements for workshop |  | 1 | 25,000 | 1 | 25,000 |
| Communication (internet + phone calls) |  | 1 | 35,000 | 1 | 35,000 |
| Subtotal |  |  |  |  | 2,560,500 |
| Activity 2: Sensitization of adolescent girls in schools on comprehensive sexuality education (CSE). |  |  |  |  |  |
| Transport Allowance for Peer Educators (PEs) to sensitize girls in school on CSE | Per PE per day | 10 | 5,000 | 8 | 400,000 |
| Token school staff assembling the school girls to receive CSE lessons | Per school staff per month | 5 | 10,000 | 2 | 100,000 |
| Subtotal |  |  |  |  | 500,000 |
| Administrative Cost |  |  |  |  |  |
| Allowance for staff |  |  |  |  |  |
| Project Coordinator | Per month | 1 | 50,000 | 5 | 250,000 |
| Project officer | Per month | 1 | 30,000 | 5 | 150,000 |
| Project Accountant | Per month | 1 | 28,575 | 5 | 142,875 |
| Office supplies |  |  |  |  |  |
| Stationaries | Lumpsum | 1 | 15, 800 | 1 | 15,800 |
| Subtotal Admin Cost |  |  |  |  | 558,675 |
| Grand Total in FCFA |  |  |  |  | 3,619,175 |
| Grand Total in USD |  |  |  |  | 6,000.05 |