Application for HER Voice Fund Grants

The HER Voice Fund provides support for the meaningful engagement and leadership of adolescent girls and young women (AGYW) and community-based organisations into Global Fund and other national and district level processes. We particularly welcome applications from organisations that can demonstrate their capacity to work with and engage AGYW from all levels including and not limited to district, regional and national level.

Grants will be made available to each of the 13 priority countries through 2020. Please note each organisation may only apply once and this must be in response to the specific call for their country.

To apply for a HER Voice Fund grant you will need to complete this application form and send it to hervoicefund@yplusnetwork.org . Please complete ALL sections below. This template must be completed in full to be considered. Please consider the following before completing the project proposal:

- Are you eligible to apply to this call?

- Be clear about what you want to achieve and how you propose to amplify the voices of adolescent girls and young women in your country and your participation in country level processes.

- Explain how the award will support AGYW to engage in policy and advocacy on issues that affect adolescent health and rights.

- Write clearly and ensure you stay within the allocated word limit. Applications which exceed the word limit will not be considered.

- Ensure the budget directly relates to outputs listed.

- Select a maximum of 2 streams of work that describe your plans

1. 	APPLICANT INFORMATION

Consent

We may as part of the application process capture personal information relating to your, sexual orientation, gender identity or HIV status or be able to infer it from the information you supply. GNP+/Y+ is committed to supporting organisations that serve affected communities and prioritise projects based on whether they are led by people from the community that they serve. We will therefore only use this information to enable us to prioritise eligibility for funding. We will not process your personal information in the future or for any other purpose.

“I agree to GNP+/Y+ processing my personal information as part of the application process” Please tick box.✓

Please click here to review our data privacy notice.

Eligibility Criteria

✓    1. Our organisation is based in one of the 13 priority countries

✓

2. Our organisation is a network or community-based organisation of adolescent girls and young women (AGYW) or young people; or a community-based organization implementing programs for AGYW and/or youth

✓

✓✓

3. Our organisation has a track record of engaging in national policy discussions, advocacy and monitoring processes relevant for Global Fund supported programs with a focus on adolescent health, HIV prevention and treatment, sexual reproductive health and rights (SRHR), empowerment of women and girls and gender-based violence (GBV).

| The name the organisation is registered as | Hope for Vulnerable Children Association |
| --- | --- |
| Any other name that the organisation is known by | HOVUCA |
| Address of the organisation | Hope for Vulnerable Children Association, P.O.Box 8257, Yaounde Cameroon. |
| Registration number with your Government and date of registration: | Number : 00001065/ARDA/J06/BAPPA Registered on: 6th August 2012 |
| Website/ Facebook page | https://hovuca.org https://web.facebook.com/hovu.ca/ |
| Number of people in organisation (include the number of paid staff and number of volunteers) | 8 Staff and 6 volunteers |
| Have you received a grant from (HER Voice Fund) before (Yes/No)? | NO |
| If you received funds previously please give the dates and a brief outline of the activities completed |  |

Representative’s Details:

Please do not send any photographs, nor provide any personal data other than contact details for yourself and for the secondary contact.

Primary

| First and Last Name: | Evelyne LUM |
| --- | --- |
| Work telephone: | +237 696 230 391 |
| Mobile telephone: | +237 677 789 855 |
| Email: | eve_lum@hovuca.org |
| Position in the organisation: | Executive Director |

Secondary

| First and Last Name: | Olive Sirri |
| --- | --- |
| Work telephone: | +237 696 230 391 |
| Mobile telephone: | +237 663 949 232 |
| Email: | olivesirri@hovuca.org |
| Position in the organisation: | Administrative Assistant |

1.1. Describe the organisation’s activities (experience) in the communities or districts you currently work in.

Please give details about your experience with the communities/districts (max 150 words)

HOVUCA has existed for 8 years with vast experience in implementing programmes for AGYW. HOVUCA’s impact work spans across 3 Regions (NW, SW and Center); 15 Districts and 25 communities. HOVUCA has reached over 12,000 AGYW directly and about 50,000 indirectly with knowledge on HIV/STIs, GBV, SRH, policies and services and skill building. A synopsis of HOVUCA’s work. HOVUCA currently runs 2 AGYW clubs called “Strong Girls Club” with funding from ALLSTARS Consultancy UK. Implemented a project on SRHR for AGYW and production of reusable pads in the Bamenda II District funded by WOMEN2030. Conducted several workshops for AGYW on the fight against HIV in 3 District (Limbe I, Mbankomo, Bamenda I) sponsored by Julie NGUM and Friends UK. Carried out a project“Reach 1000 AGYW with Female Condoms Project” sponsored by CRTG Yaounde. Implemented a research project on SGBV in the Mbankomo District funded by MACUDA, UAE

1.2. Please name the staff who will be involved in the project and their positions

1) Evelyne LUM : Project Coordinator

2) Catherine AWA: M & E officer:

3) Loveline NGUMBI : Account Officer

4) Beatrice NCHE ETUBA: Community Mobilizer/Field Facilitator

5) Sirri Olive: Administrative Assistant/logistics officer

6) Dr. Derick TSE NJI: Medical Consultant

7) ANGWE Loveline: Community Mobilizer/Training Coordinator

8) Charlotte ABA S.: Communication Officer

2. 	FUNDING REQUEST INFORMATION

Please tick a maximum of 2 work streams your work is related to; (for detailed descriptions see the HER Voice Fund website page: http://www.yplusnetwork.org/hervoicefund/

✓   1. Collecting information and stories for AGYW advocacy

✓   2. Training and mentoring for policy and advocacy work

3. AGYW Engagement in policy and advocacy

4. Monitoring and accountability.

| Project Title/ Topic (Max 25 words) | Creating Safe Spaces for AGYW Living with or at Risk of HIV to Access Better SRH Services and Advocate for their SRHR. |
| --- | --- |
| Grant amount requested in EUROS /Equivalent Local amount The amount requested should not exceed 9,000 EUROS | 8,828 USD / 4,855,400 FCFA |
| Location of the Activities Indicate country, district, city or village | Cameroon, Yaoundé III Municipality |
| Project dates Please include start and completion dates (No activities should be implemented until the outcome of your application is received) | 2nd of May 2020 to 30th April 2021 |

2.1. Describe the overall goal for your project (50 words)

The goal is to educate AGYW in the Yaoundé III Municipality On HIV/SRH and create a supportive environment for them to speak out and also strengthen their capacity for advocacy for improvement in SRH services and HIV/SRH polices that will meet their SRH needs to cube the rate of HIV.

2.2 What are you trying to achieve with your project (max 250 words) Please list your objectives and ensure that they are aligned to your project goal

- To provide comprehensive education and information to AGYW about HIV/SRHR and related national policies targeting directly 100 AGYW aged 14 – 24 years. - To carry out a research on barriers to accessing HIV/SRHR and services, targeting 300 interviewee AGYW in the Yaounde III Municipality. - To create safe spaces where AGYW will: feel comfortable to discuss issues about their lives without the fear of judgment or harm; learn to express confidently in public; how to develop advocacy for policy change. - To raise public awareness and advocate for government and community participation for the enforcement of HIV/SRH policies targeting at least 10,000 indirect beneficiaries of all categories and ages (decision makers, men, women, boys and girls) - To bring local government authorities, influencers including opinion leaders decision makers, policy makers, service providers and CCM representatives into contact with AGYW to review the situation of SRH and policy implementation gaps at the district level and engage AGYW in the design and implementation of programmes.

2.2. Activities to be implemented (Please describe the project activities with clear timelines.)

Activity Sets by Project Objectives Objective 1: To provide comprehensive education and information to AGYW about HIV/SRHR and related national policies targeting directly 100 AGYW aged 14 – 24 years. Activity 1: Preliminaries for project kickoff (Timeline: May 2020) - Obtaining administration documents (permit): Making contacts with local District authorities to obtain permission to carry out project in the district. - Organizing a project kickoff meeting for HOVUCA staff and project team members: A planning meeting will be organized for HOVUCA staff, volunteers including some AGYW. The aim of the meeting is to clearly explain to staff and project team members the project’s terms of reference to ensure high-quality deliverables throughout the duration of the project. - Community entry, Mobilization and selection of project participants and stakeholders: stakeholders for the startup workshop will be contacted and given letters of invitation for the startup workshop. Activity 2: Organize and conduct a startup Workshop to launch the project. (TimeLine: May 2020) Prior to the start of the project, a buy-in startup workshop will be held with all key stakeholders. It will bring together 40 participants including: local government representatives, district health HIV/SRH service providers, AGYW who are representatives of youth associations and clubs, global fund representative, representative of the Regional Technical working group for the fight against HIV/AIDS, CBOs, INGOs working on HIV/SRHR, teachers from schools, colleges and universities, research organizations and institutions clergy men and traditional leaders. The purpose of the workshop is for better planning and coordination. Specifically, the workshop is purposed for shared perspectives on project goals, intended outcomes, solid plan for moving forward, reduced project risk, minimize duplication of efforts, share of best practices and increased probability of project success. Activity 3. Conducting a Three Days Education Workshop for 100 AGYW on HIV/SRHR, services and related Policies. (Timeline: June 2020). Many AGYW lack comprehensive knowledge on HIV/SRHR, services and polices. This is the reason why we will be organizing this 3 days workshop that will impact knowledge on HIV/SRHR, services and polices to 100 AGYW aged (14 – 24) in the Yaoundé III Municipality. The project opted for 3 days training because of barriers imposed by COVID – 19. As a preventive measure to the disease the government passed a law prohibiting gathering of more than 50 people. In addition, because HOVUCA holds to the principle of “Do No Harm” the project will host 33 AGYW for each day of the workshop to keep them safe from Coronavirus. AGYW who are the major beneficiaries will include: those living with HIV and those at-risk of HIV, AGYW with disabilities, in and out of school AGYW, university students, teenage mothers etc. Participants for the workshop will be carefully selected and will be those that belong to large groups, like social youth groups, church youth groups, and leaders of clubs. This pattern of selection is used so that after the training, beneficiaries will then act as champions and educate members of their groups or institutions thereby increasing the reach of AGYW with knowledge on HIV/SRHR, services and policies. The method of workshop delivery will include: PowerPoint presentations, lectures, focus group discussions, questions and answers and projection of images/videos, songs and role play. Objective 2: To carry out a research on barriers to accessing HIV/SRHR and services, targeting 300 interviewees AGYW in the Yaounde III Municipality. Activity 4: Conduct a research on Barriers faced by AGYW in accessing HIV/SRHR Services (Timeline: August 2020 – September 2020). A research on barriers faced by AGYW in accessing HIV/SRHR services and gaps in policy implementation will be carried in the Yaounde III Municipality. This research targets 300 AGYW aged 14 – 24 and the methodology for the research will be through focus group discussions and key informant interviews. A consent form to obtain the research sample will be developed and the interviewee will read and sign to show that she agrees to be interviewed. The primary objective of this exercise is to get stories from AGYW about the problems they face in upholding their HIV/SRHR and to identify policy gaps. The findings of the research and the gaps identified will be used to advocate for better policy reforms that will meet the health needs of AGYW. Objective 3: To create safe spaces where AGYW will: feel comfortable to discuss issues about their lives without the fear of judgment or harm; learn to express confidently in public; how to develop advocacy for policy change. Activity 5: Establishment and running of AGYW HIV/SRH Forum called Ambassadors Forum (Timeline:September 2020 – March Time 2021). This activity will run for 7 months and is aimed at broadening the horizons of AGYW on matters that affect their lives. The Ambassadors forum will bring together 20 -25 selected AGYW and sessions will be holding once a week. The AGYW Ambassadors forum will have 2 mentors who will be delivering short training sessions on a variety of topics. Mentorship will adopt a holistic approach through which training will address HIV/SRHR, policies, services and social determinants leading to improve knowledge, confidence and self-esteem. AGYW will learn how to develop advocacy messages and also receive capacity building training in public speaking since they will be participating in the radio dialogue and advocacy programme and the social media space that will be created. They will also be trained as peer educators and ambassadors for the promotion of sexual and reproductive health and rights and fight HIV/AIDS. Other forum activities will include drama, arts and role play geared for advocacy. Activity 6: Creation and Running of a HIV/SRH Social Media space (page): (Timeline: September 2020) Social media has a wide coverage, is cost effective and gives timely messages. In addition, it appeals to some sections of society particularly the young generation. As such, the project will reach a wider population of AGYW with key messages on HIV/SRH. In collaborate with the AGYW, the most appropriate social media platform will be chosen and account created. The platform is aimed at narrative building by articulating the perspectives of AGYW in their diversity on HIV/SRHR including GBV and women and girls empowerment. Periodic themes and topics will be posted for discussions. There will be interactions on questions and answers on HIV/SRH, sharing of experiences and good practices. Drama/sketches that passes out key messages on SRH and fights stigma on HIV will be posted. Youth groups/clubs and other social groups of young people will be mobilization to join the platform for discussion. Duty bearers could use these platforms to generate, analyze and disseminate HIV/SRH information to guide policy and planning for various levels. On the other AGYW can use the platforms to share their experiences and voice out their grievances for action. Activities on the social media platform will be coordinated by selected AGYW from the Ambassador Forum with guidance from project team and mentors Objective 4: To raise public awareness and advocate for government and community participation for the enforcement of HIV/SRH policies targeting at least 10,000 indirect beneficiaries of all categories and ages (decision makers, men, women, boys and girls) Activity 7: Organizing and conducting an FM radio dialogues and advocacy on HIV/SRHR policy reforms targeting about 10,000 indirect beneficiaries Timeline (September 2020 – March Time 2021). This will be a monthly live radio broadcast conducted from the FM radio and will run for seven (7) months with an aim of “getting the public talking” about HIV/SRHR, access to services and barriers. Consultations will be made with other NGOs working on HIV/SRH to develop appropriate topics/themes to be discussed in the radio dialogue/advocacy. A mapping of FM Radio stations will be conducted to select the radio station which has the highest listenership and the project will build the capacity of the representatives of the FM Radio station to engage in HIV/SRH communication including the use of appropriate language and positive portrayal AGYW and providing a platform for government accountability and advocacy amongst the AGYW and the wider community. The project will also hold monthly interactive discuss meetings with mentors, AGYW and other stakeholders to discuss pre-determined topics/themes on HIV/SRHR and policy gaps. Community members will be mobilized to take part in the Monthly HIV/ SRHR and policy discourse meanwhile the District representative of Ministry of Public Health will have access to the FM Radio programme provided by the project to communicate information on HIV/SRH and services. Objective 5: To bring local government authorities, influencers including opinion leaders decision makers, policy makers, service providers into contact with AGYW to review the situation of SRH and policy implementation at the district level to inform policy decisions Activity 8: Organize and conduct a consultation meeting with local government and decision makers. (Timeline September 2020). This consultation meeting will be a one day round table meeting that will bring together selected AGYW in contact with technical experts, public health officials, STI/HIV program managers, and SRH program managers, local and international NGOs working with adolescents and youths on HIV/SRHR Sexual as well as faith-based organizations and the media. The meeting will focus on review of policy documents and sharing of experiences with access to SRH services and identification of gaps, good practices and lessons learned in other countries in addressing SRH for AGYW, and engagement in a dialogue to jointly identify strategic action as well creating links between the District health providers and AGYW for SRH services. Prior to the consultation meeting, a background document will be prepared that summarizes available relevant information on the different aspects of SRH for AGYW. The background document will be shared with meeting participants prior to the meeting, to facilitate an informed dialogue. The methodology in the meeting will include presentations, plenary and small group discussions. Other Project Activities include: Activity 9:. Monitoring and evaluation (M & E) Timeline (May 2020 – April 2021). Monitoring will be done by activity and also monthly monitoring and reports by staff/volunteers. A mid-term evaluation shall be made to assess the progress made with resources to determine whether project goals and objectives have been met. A final participatory impact assessment will be made to assess the level of impact of the project on both the intended and non-intended beneficiaries. We shall use the Project goals as reference, and will also use photos to track the results. Group discussions will form part of the participatory monitoring methodology. Activity 10: Documentation and Reporting. Timeline (May 2020 – April 2021). We will document all project activities including monthly and mid-term reports for HOVUCA’s record. We will report to donor but also, reporting will be in accordance with their reporting guidelines

2.3. How will you know your project has been successful? (max 200 words) Please list your project outcomes and describe 3-5 indicators you will use to monitor this.

Outcomes Outcome for objective 1 Increased knowledge on HIV/SRH for 100 AGYW and increased access to essential HIV/SRH resources, information and services. Outcome for objective 2 Barriers on HIV/SRH and rights of AGYW identified as well as policy gaps and advocacy plan developed. Outcome for objective 3 AGYW of the Ambassador Forum have broaden their horizons on HIV/SRHR and health policies and have acquired skills in leadership, public speaking, advocacy and peer to peer education. Outcome for objective 4 Increased awareness on HIV/SRH with about 10,000 community members (men, women, boys, girls) who received key messages on HIV/SRHR Outcome for objective 5 Outcome i: Increased opportunity for AGYW to participate in constructive and critical conservative with local government and health service providers on HIV/SRHR Outcome ii: Law and policy on HIV/SRH and rights adolescent and young people is reviewed, reformed. INDICATORS 1) % of AGYW accessing HIV/SRHR friendly services in the district and adopting safe SRH behaviors. 2) Rigorous advocacy undertaken. 3) % increased of men, women, boys, girls reached through FM Radio program with key messages on HIV/SRHR 4) % decrease in adolescent/early pregnancies, New HIV/STIs infection. 5) Inclusion of research findings recommendations in policy decisions/ proposals/ reviews

## 3.	BUDGET

| Category | Activity | Cost/ Currency |
| --- | --- | --- |
| Staffing | Remuneration for staff | 1,000$ |
|  | Stipends for AGYW | 1,200$ |
|  | Token for Project Resource persons(mentors and workshop trainers) | 1,000$ |
| Travel costs | Transport for stakeholders to attend the startup workshop (project launch) | 280$ |
|  | Transport for participants (AGYW) to attend the HIV/SRHR awareness/education workshop | 200$ |
|  | Transport for participants (AGYW)for the FM.Radio Dialogue/Advocacy program | 200$ |
|  | Transport for volunteers/AGYW to carry out the research activity | 300$ |
|  | Transport for community mobilizer for community mobilization. | 90$ |
|  | Transport for 10 AGYW to participate in the round table consultation meeting with policy/decision markers. | 50$ |
| Materials/ publication/media | 3 Banner for:(startup workshop, awareness workshop and Round table consultation meeting) | 180$ |
|  | Purchase of training materials, hire of equipment and writing materials for participants (All for the 5 different workshops) | 380$ |
|  | T-shirts with advocacy messages for 100 AGYW | 400$ |
|  | Reproduction of training Manuals and handouts (policy documents and other relevant materials) | 250$ |
| Workshops and Meetings | Startup Workshop/Project Launch with stakeholders | 380$ |
|  | Consultation with local government/policy/decision makers | 305$ |
|  | Conducting three days education workshop for 100 AGYW on HIV/SRHR, SERVICS AND Policies | 940$ |
|  | Establishment and running of AGYW Ambassador Forum (7months) | 350$ |
|  | Conducting Research on barriers for AGYW faced in accessing HIV/SRHR | 200$ |
|  | Conducting a FM Radio Dialogues and advocacy on HIV/SRHR (7 months) | 280$ |
| Administration/ Office costs | Stationaries | 200 |
|  | communication | 240 |
|  | logistics | 403 |
| Total |  | 8,828$ |

## 4.	BANK INFORMATION

| Name of Bank | United Bank for Africa, Cameroon |
| --- | --- |
| Bank SWIFT Code or IBAN | UNAFCMCX Country Code CM21 Bank Code10033 05207 |
| Corresponding Bank if applicable |  |
| Bank Address | United Bank for Africa Cameroon, Hippodrome P.O.Box 1029 Yaounde Avenue Des Banques |
| Name of Account Holder | Hope for Vulnerable Children Association (HOVUCA) |
| Account Number | 07031000336 - 60 |

## 5.	REFERENCES

Please provide details of 2 referees who can provide information about the work you do with AGYW and your engagement with local, district and or national policy and advocacy processes.

| Name of referee | Nwana Richare M. |
| --- | --- |
| Organization | Association Camerounaise Pour Le Marketing Social (ACMS) |
| Email | rnwana@acms-cm.org |
| Telephone number | +237 677 412 025 |

| Name of referee | Tanda Godwin Ade |
| --- | --- |
| Organization | Environmental Protection and Development Association |
| Email | godwin@epdacameroon.org |
| Telephone number | +237 677 227 766 |

Please provide, along with your application, the following documents:

  - A copy of the Certificate of Registration from your organisation

  - A Copy of the I.D /Passport of the organisation/group/network head.

Signature:			_________________________

Date (DD/MM/YY): 		_______15/04/2020__________________