HER Voice Fund – Application Form

The HER Voice Fund is implemented by the Global Network of Young People Living with HIV (Y+ Global), with support from the Global Fund to Fight AIDS, Tuberculosis and Malaria (the Global Fund) and ViiV Healthcare Positive Action, to strengthen the meaningful engagement and leadership of adolescent girls and young women (AGYW) in decision making spaces with the aim of reducing HIV incidence and improving our broader health, wellbeing and rights.

Particularly, what we want to see in 2023 is:

- Demonstrate the leadership and expertise of AGYWs influencing change on structural systems, punitive laws and policies, gender and harmful norms that are related to our health and rights in our diversity (for example, AGYWs being engaged in Global Fund Grant Cycle 7 (formally known as NFM4)  informing the Funding request, responding to comments from the Technical Review Panel, engaged at grant making level and follow through to see how many AGYW led org will receive funding and feedback loop to the AGYW communities on Grant Cycle 7 (GC7)approved priorities)

- Advocacy campaigns that amplify and action the relevant issues of AGYW in our diversity with a strong desire to promote collaboration and movement building and which can contribute to influencing processes and policies that relates to AGYW health and well-being. (For example, PEPFAR COP Processes, Grant Cycle 7/NFM4, AU platforms, UHC, different policies)

- Continued ethical and meaningful participation of adolescent girls and young women in our diversity in relevant decision-making processes, monitoring implementation and evaluation of AGYW programs, contributing to community led monitoring processes.   championing the national and district level activities that speak to the realities of AGYW and align to three overarching aspirations.

- Promote digital equity, making sure AGYWs benefit and have access to real time information and safe space interactions on key issues that affect our health and rights.

Grants will be made available in all 13 priority countries (Botswana, Cameroon, Eswatini, Kenya, Lesotho, Malawi, Mozambique, Namibia, South Africa, Tanzania, Uganda, Zambia and Zimbabwe) through 2023. Please note that the funding is for AGYW, between the ages 15 to 28, including AGYW living with HIV, AGYW living with disabilities, those who identify as Lesbian, Gay, Bisexual, Transgender, Intersex, Queer (LGBTIQ+), AGYW in conflict-affected zones, those in rural areas, AGYW who inject/use drugs, AGYW who sell sex, pregnant AGYW and young mothers.

To apply for a HER Voice Fund grant 2023, you will need to complete this application form and send it to hervoicefund@yplusglobal.org Please note that ALL sections in this template must be completed in full to be considered. Please read through the entire application form first and consider the following before completing the form:

- At least two AGYW must be meaningfully involved throughout the writing, finalization and submission of the application process. We encourage collaborations with country leads and HER Voice Fund Ambassadors when developing this proposal.

- Select at least one (maximum two) Country Aspiration/s amongst the three below that your project goal will align with.

- The project goal and objectives should clearly align with the HER Voice Fund Strategy 2022-2025 and align to aspirations articulated in the relevant country profile.

- Clearly show how you will measure the goals and objectives by articulating SMART outputs and outcomes, aligning with country aspirations and the HER Voice Fund strategy.

- Clearly explain how you intend to support AGYW to be part of the key decision-making processes at the district or national level (for example, technical working groups, CCMs, NSP or AGYW strategy review), and the focus of advocacy related to our HIV prevention, SRHR or broader health and rights needs.

- Ensure the budget activities directly relate to the goals and objectives you have chosen. Please note, your budget should allocate a minimum of up to 75% to activity costs and a maximum of up to 25% to administration costs.

- Write clearly and ensure you stay within the allocated word limit. Applications that exceed the word limit will not be considered.

- Make sure your application is signed by the executive director, unsigned application will not be considered. Please send us a signed PDF form and a word document version

- The Application Submission is due to the Country Lead and Ambassador on the 10th of March 2023. PMU deadline is on the 15th of March 2023 at 23:59 hours (CAT). Applications received after this deadline will not be considered.

1. 	APPLICANT INFORMATION

Consent

As part of the application process, we may capture personal information relating to your sexual orientation, gender identity or HIV status or be able to infer it from the information you supply. Y+ Global is committed to supporting organisations that serve affected communities and prioritise projects based on whether they are led by people from the community that they serve. We will, therefore, only use this information to enable us to prioritise eligibility for funding. We will not process your personal information in the future or for any other purpose.

✓

“I agree to Y+ Global and ViiV Healthcare Positive Action processing my personal information as part of the application process” Please tick the box.

Please click here https://viivhealthcare.com/en-gb/privacy-notice/ to review the ViiV Healthcare data privacy notice.

| The name the organisation is registered as | Hope for Vulnerable Children Association |
| --- | --- |
| Any other name that the organisation is known by | HOVUCA |
| Address of the organisation | P.O.Box 8257, Tam Tam Yaounde, Cameroon |
| Registration number with your government and date of registration: | Number: 00001065/ARDA/J06/BAPPA Registered on: 6th August 2012 |
| Website/ Social Media platforms | Website: https://hovuca.org Social Media Platforms Facebook: @hovu.ca Twitter: @hovuca1 Instagram: @hope_for_vulnerable_children |
| Number of people in the organisation (number of paid staff and number of volunteers) | Number of people in the organisation 6, number of paid staff 3, number of volunteers 4 |

Representative’s Details:

Please do not send any photographs or any personal data other than contact details for primary and secondary contact. Please list the primary person who will be the focal points of the HER Voice Fund, a secondary person being the person responsible for Finance.

Primary

| First and Last Name: | LUM Evelyne |
| --- | --- |
| Work telephone: | 00237 696 230 391 |
| Mobile telephone: | 00237 677 789 855 |
| Email: | Eve_lum@hovuca.org |
| Position in the organisation: | Executive Director |

Secondary

| First and Last Name: | NGUMBI Loveline |
| --- | --- |
| Work telephone: | +237 696 230 391 |
| Mobile telephone: | +237 670 074 923 |
| Email: | ngumbilove@yahoo.com |
| Position in the organisation: | Finance Officer |

  - Describe your organisation’s strategic focus area(s) (max 100 words)

HOVUCA works with children with a special focus on girls. Its strategic priority areas include: child protection, education, health and humanitarian response. Our work in the child protection priority area, focuses on protecting children especially the girl child from all forms of violence, abuse, neglect and exploitation. Under health and education, we work on HIV and AIDS and focus on Prevention of Mother-to-Child Transmission (PMTCT), HIV-Free adolescent as well as adolescent reproductive health and family planning. Our humanitarian response work focuses on internally displaced adolescent girls and boys as we contribute to meeting their basic needs.

1.2. Please list the population(s) your organisation works with (max 100 words)

-Children
       - Girls,
       - Adolescent girls and young women
     - Young women and girls with disabilities,
     - Girls affected by conflict like the internal displaced adolescent girls and young women,
     - children, adolescent and young women living with HIV and those at risk of HIV.
     - Caregivers/guardians

1.3 Describe the context in which the HER Voice Fund project will continue to be implemented (max 100)

Aspirations 2 and 3 for AGYW in Cameroon demands for reduced GBV, promotion of gender equality, HIV prevention and access to SRH services, our 2023 HVF project is aligned to these aspirations. Our HVF project also aligns with the core principles of the HVF strategies as it targets AGYW in their diversity, fights human rights violations against AGYW and will be advocating for gender equality. It also aimed at building the leadership of AGYW to meaningfully participate and contribute in Global Fund and HIV/SRH national processes.

2. 	FUNDING REQUEST INFORMATION

Impact: Adolescent girls and young women benefit from rights based and gender transformative laws, policies, practices and programmes, resulting in a reduction in HIV incidence and improvements in our broader health, wellbeing and rights.

Objective 1: To provide grants in 13 priority countries to support AGYW to participate and exercise leadership in key decision-making spaces at all levels that affect our health and rights. These include Country Coordinating Mechanism (CCM) and Country Operational Plan (COP) meetings, National Strategic Plan (NSP) consultations, Technical Working Groups (TWGs) and other fora related to HIV, sexual and reproductive health and rights (SRHR), gender, and violence against women and girls.

Select at least one (maximum two) Country Aspiration/s amongst the three below that your project goal will align with.

| Themes | Please tick or highlight the box |
| --- | --- |
| Increase access to and quality of programmes and services for AGYW – by scaling up programmes, interventions and referral mechanisms related to AGYW in the HIV response, including gender-based violence services, integrated HIV and SRH services and the provision of comprehensive sexuality education. |  |
| Improve the social, cultural and legal environment for AGYW – by addressing socio-cultural constraints and economic factors that drive gender inequalities and predispose AGYW to gender-based violence and HIV infections; and by influencing relevant policy and legal frameworks. | ✓ |
| Increase empowerment and participation of AGYW –promoting AGYW participation in national HIV and SRH programming and policy implementation, monitoring implementation and evaluation of AGYW programs, contributing to community led monitoring processes | ✓ |

2.1. Describe the overall goal for your project, aligning with the impact of HER Voice Fund and themes selected above (50 words)

The goal of this project is to improve communication and leadership skills of AGYW in SRHR advocacy and to reduce the incidence of GBV and HIV amongst AGYW in Mfoundi Division.

2.2 What are you trying to achieve with your project (max 250 words)? Please list your SMART objectives and ensure that they are aligned to your selected themes above)

- To mobilize communities to learn, reflect and fight against deep rooted patriarchal ills including: all forms of inequalities, early and forced marriage, forced sterilization, forced abortion, myths about menstruation and repressive gender roles to ENABLE AGYW have control over their sexuality, health and rights and reduce their vulnerability to new HIV infections by January, 2024.

- To promote and sustain community participation and AGYW actions in the prevention of GBV and promotion of SRHR through a multimedia strategy AIMED at: a zero tolerance to GBV amongst communities and enhancement of SRHR of AGYW by December, 2023.

- To support and engage AGYW to review national SRHR and HIV policy/guidelines, analyze them, identify policy gaps and advocate for SRHR and HIV policy reforms that GIVES AGYW an enabling environment to access quality SRHR and HIV services by October 2023

- To ensure the participation of AGYW in national and community-led HIV processes and programmes, HIV committee meetings of line ministries, TWGs, NSP and meetings related to the Global Fund Processes by December 2023

2.2. Please list activities to be implemented (Please submit a separate and more detailed Implementation plan describing the project activities with clear timelines.)

| Activity | Date | Specific action plans in more details |
| --- | --- | --- |
| 2023 Project start-up/launch with key stakeholders | May, 2023 | Project launch meeting with key stakeholders is pivotal at HOVUCA, this is from lessons learnt. The meeting open doors for meaningful collaboration. It facilitates negotiation for future activities to happen. It clears the way and eases acceptance of AGYW’s participation and contribution in their platforms. Thus, prior to the start of the 2023 project, we will organize and conduct a 1 day buy-in start-up meeting to launch the 2023 HER Voice project. It will bring together 30 participants including: key stakeholders and 15 AGYW (both old and newly recruited). For stakeholders, we will particularly implicate those relevant to our advocacy theme and who are vital to help advance our 2023 objectives. Specifically, we are looking at stakeholders from line ministries like the ministry of health (MINSANTE) particularly the department of family health, ministry of women’s empowerment and the family (MINPROFF), Ministry of Social Affairs (MINAS) Ministry of Justice. We are also looking at Global fund stakeholders like the Principal Recipients and Sub recipients who are influential in the Global Fund processes. Most importantly, we will implicate cultural leaders as they are the ones who promote gender inequality and cultural beliefs and practices that perpetuate GBV as well as religious leaders who are a hinderance to access to SRHR and services. UN agencies will not be left out – UNAIDS, UNFPA, UN women. CBOs of key populations and PLWHIV will also be part of this project launch and also heads of schools and teachers. The purpose of the start-up is for better planning and coordination. Specifically, the workshop is purposed for shared perspectives on project goals, intended outcomes, solid plan for moving forward, share of best practices increased probability of project success. AGYW ambassadors both old and the newly recruited will also be able to capture the project goal and objectives and will be expose to the stakeholders as we intend to engage AGYW to participate and contribute in stakeholders’ platforms. |
| Conduct a desk review, develop an advocacy brief and organise a briefing Meeting | June 2023 – October 2023 | For this activity, AGYW in collaboration with a HOVUCA staff will be supported to conduct a Desk review to identify punitive laws and policies that hinder AGYW in their diversity to access HIV/SRHR and services and protective internationally binding human right laws. Thereafter, based on gaps identified, they will develop advocacies for legal support and increase access to justice for AGYW especially for AGYW key population, and enforcement of policies against GBV and other social/cultural norms. In this process we will implicate a resource person to guide us in the process of desk review and development of an advocacy brief. In the end a briefing meeting will be organised with legal and policy stakeholders including stakeholders from line ministers, cultural and religious leaders for lobbying and collaboration to address legal and policy barriers preventing AGYW particularly AGYW Key population from exercising their SRHR. |
| Support the participation and contribution of AGYW in national, community – led and Global fund processes | July 2023 – Dec 2023 | AGYW will be supported to participate in different national HIV/SRHR and GBV platforms and contribute either through a presentation or verbal contribution. Prior to participation, AGYW need to be mentored to get them participate meaningfully, as such we will solicit the services of a mentor(s) to accompany AGYW in the process. The mentor sessions will happen at different times depending on the platform for participation and the dates to keep the AGYW mentee with fresh and accurate knowledge. We have earmarked some platforms where AGYW voices can be captured in decision making including: TWG on STIs, elaboration of the new National Strategic (NSP),Review of health manuals for school, during HIV committee meetings of any of the line ministries, during National design and planning of related international days commemoration e,g world AIDS Day, persons with disability world day, youth platforms organized by the National Assembly. AGYW will also participation online in the GC7 Funding quest review sessions |
| Multimedia Campaign to fight against gender inequality and promotion of digital leadership for AGYW | July 2023 – Dec 2023 | Despite efforts that have been made to fight against gender inequality and harmful cultural practices that hinder the enjoyment of AGYW SRHR, many forms of GBV and violation of human rights and SRHR of women and girls continue to be perceived as private, relatively unimportant or a normal part of life. A multimedia campaign has been seen as a powerful tool to bring change. Therefore, this multimedia strategy is aimed at reaching state and non-state duty bearers who have the power to change the narrative with key advocacy messages and information to cause them to bring change, it is also aimed at promoting the social media and digital leadership amongst AGYW. This multimedia campaign strategy will be on: social media (Facebook, twitter, YouTube), web blog and TV. It will solicit the assistance of digital tech expert who will give AGYW skills on the use of the different platforms and how to lead on the different platforms |
| Run to Debunk harmful cultural practices | August 2023 | Run to Debunk harmful cultural practices, is an advocacy Run which is aimed at engaging community members to debunk myths, norms, and sociocultural barriers which impede AGYW from enjoying their SRHR and participate in the promotion of SRHR. The advocacy Run will call the attention of legal and traditional rights custodians to harmful practices and policies impeding AGYW from enjoying their inviolable right. The mobilization strategy will be “one parent, one AGYW” for a Run to fight against criminalized laws and harmful traditional practices. 8,050+ beneficiaries are targeted for this activity – 50 direct beneficiaries who are the runners and 8,000+ indirect beneficiaries (onlookers or eyewitnesses during the Run). Also, during the Run, awareness will be created through printed messages on the Run T-shirts and key awareness and advocacy messages on placards and through songs. Target audience for the advocacy activity will be community members (men and women, with their daughters, nieces or any AGYW around their corner) chiefs of the project host community and more importantly the IDP chiefs as most of the norms we shall be advocating for change are perpetrated in some areas in the conflict regions e.g FGM is mostly perpetrated in the Ejagham community in the South West conflict Region. Representatives from the frontline ministries will also be invited for the advocacy Run. The Run will end up at an open space where we will have short interactive sessions where key information and messages will be delivered to the Runners and opinion and views of the runners will be shared for a way forward. |
| Building AGYW SRHR advocates in schools | September 2023 – January 2024 | “AGYW need what is lacking” to stand up for their rights. They need knowledge on their health rights including knowledge on human rights in combination, they need the skills to enable them stand up for their rights. School is the biggest platform where we can find them and create a huge impact. Lessons learnt: i) when AGYW in schools know their sexual and health rights and have the skills, they make healthier choices, resist negative pressures and avoid risk behavior which all reduces their vulnerability to HIV infection and STIs ii) when AGYW are trained, mentored and supported, they become the most effective advocates for their rights. It is on this basis that we are taking SRHR to AGYW in schools. This activity will take place in 5 schools targeting over 2000 AGYW to impart them with knowledge and skills on SRHR, GBV, School Related Gender Based Violence (SRGBV), Human rights, gender equality and social Justice. These topics will be delivered in schools by trained and mentored AGYW |
| HOVUCA - AGYW Participation in the National AGYW summit | October 2023 | Since 2020, AGYW under the HVF project in Cameroon have been working in isolation and advocating for their rights using different approaches and now is about time to bring efforts together and make advocacy big. This “National AGYW Summit” is aimed at convening AGYW of HVF Grantees in Cameroon in a summit for new energy, fresh ideas and inspiring advocacy approaches that will accelerate elimination of harmful cultural practices and gender inequalities that inhibit AGYW from enjoying their full SRHR and access to HIV services. HOVUCA’s 2 AGYW including one staff will be attending and contributing in this movement building amongst HVF AGYW in Cameroon. |

2.3. How will you know your project has been successful? (Max 200 words) Please describe the indicators you will use to monitor and measure progress and achievement. Your indicators must align with the goal, objectives and activities above

Indicators

- # of community members with key information about GBV and who are contributing in GBV prevention and reporting cases of GBV. # of community members who have Refrain from cultural and Community practices that promote gender inequality e.g. forced marriages, FGM, or Child marriages

- # of AGYW actively on different media platform leading Advocacy; #of content developed, # of views, likes and virality rate on social media #of articles/awareness/advocacy messages posted on the HOVUCA SRHR/HIV Blog

- # of national SRHR/HIV policy including international human rights documents review, # of punitive laws and policies identified relating to AGYW of key population # of advocacy briefs developed and presented

4. # of AGYW who have participated in national and Global fund processes and # of HIV committee meetings of line ministries, NSP, TWGs where AGYW participated and made contributions or presentations.

5.

2.4 Briefly describe how you are going to continuously engage key stakeholders, especially government line ministries, regarding the HER Voice Fund project you are going to implement (e.g., submitting monthly reports) (Max 80 words)

We will engage the line ministries by submitting monthly/or quarter and final reports of activities of the project and invite them to participate in our events, e.g., the project launch meeting where we will establish a working relationship. We will ensure AGYW participate in national SRHR and HIV programmes e.g., TWGs, NSP. We will engage community members and leaders by ensuring they participate in some of our activities e.g., the Run to debunk norms activity.

## 3.	BUDGET

Please fill out the provided template excel document, providing information budget which can start from 14 April 2023 and ends on or before February 2024. The Her Voice Fund is a grassroot grant; please ensure that you do not include any capital expenditure costs in your budget, e.g. assets, laptops or cameras. Activity costs should be a minimum 75% of the whole budget, and administration costs a maximum 25% of the budget. Please note: your budget should be to a limit of 8000 Euros

4.	BANK INFORMATION

| Name of Bank | United Bank for Africa (UBA) Cameroon |  |
| --- | --- | --- |
| Bank SWIFT Code or IBAN | UNAFCMCX, CM21 10033 05207 07031000336 60 |  |
| Corresponding Bank if applicable |  |  |
| Bank Address | United Bank for Africa Cameroon, Hippodrome, P.O. Box 1029 Yaoundé, Avenue Des Banque |  |
| Name of Account Holder | Hope for Vulnerable Children Association (HOVUCA) |  |
| Account Number | 07031000336 |  |

## 5.	REFERENCES

Please provide details of 2 referees who can provide information about the work you have done with AGYW and your engagement with local, district, and national policy and advocacy processes.

| Name of referee | Dr. KOB David |
| --- | --- |
| Organization | UNAIDS |
| Email | kobyesameiii@unaids.org |
| Telephone number | +237 677 667 499 |

| Name of referee | BOLIMA NANCY |  |
| --- | --- | --- |
| Organization | Health Development Consultancy Services (HEDECS) |  |
| Email | nancyakwi@yahoo.com |  |
| Telephone number | +237 677 673 878 |  |

Signature:			_________________________

10/03/2023

Date (DD/MM/YY): 		_________________________

SMART stands for Specific, Measurable, Achievable, Relevant, and Time-Bound